## Summary
Masters | Item No. | Mapping | Conversion Date | Data Pull | Manual Clean Up Required? | Data Services Responsible Party | Business Responsible Party | Completion Date
New Buisness Unit Setup | 4 | 2019-12-01 | 2020-01-10 | 2020-01-02 | Yes, decision Property Numbers |  | Kara Wood
All Non Well Properties (Batteries, Allocations, Gathering Sys, etc.) | #N/A | 2019-12-07 | 2020-01-10 | 2020-01-02 | Yes, decision Property Numbers | #N/A | #N/A
Cost Center, Properties, Wells, Cost Center Hierarchy | 6 | 2019-12-02 | 2020-01-10 | 2020-01-02 | Yes, decision Property Numbers | Nick Bray | Taylor Bishop
Business Associates Master Risk | 9 | 2019-12-02 | 2020-01-10 | 2020-01-02 | Yes, duplicate BA's | Davison Oliver | Josh Owens
Business Associates Master GWI Land | 10 | 2019-12-02 | 2020-01-27 | 2020-01-24 | Yes, duplicate BA's | Davison Oliver | Donald Harrell
Business Associates Master Land NRI | 11 | 2019-12-02 | 2020-01-27 | 2020-01-24 | Yes, duplicate BA's | Davison Oliver | Donald Harrell
Inventory Stock Item Master | 15 | 2019-12-09 | 2020-01-27 | 2020-01-24 |  | Quorum Support | Kevin Hays
AFE Master | 13 | 2019-12-02 | 2020-01-27 | 2020-01-24 | Yes, AFE number decision | Quorum Support | Kathleen K
JIB Cost Allocations | 23 | 2019-12-12 | 2020-01-27 | 2020-01-24 |  | Quorum Support | Kathleen K
Asset Master | 26 | 2019-12-19 | 2020-01-27 | 2020-01-24 |  | Quorum Support | Courtney Roach
Division of Interest (JIB) | 24 | 2019-12-16 | 2020-01-27 | 2020-01-24 |  | Davison Oliver | Donald Harrell
Division of Interest (Revenue) | 39 | 2019-12-30 | 2020-03-05 | 2020-03-02 |  | Davison Oliver | Donald Harrell
Current Transaction Data |  | Mapping | Conversion Date |  | Manual Clean Up Required? | Data Services Responsible Party | Business Responsible Party | Completion Date
Open Invoice History | 27 | 2020-01-06 | 2020-01-27 | 2020-01-24 |  | Michael Shiraz | Kathleen K
Open Invoice Price Books | 30 | 2020-01-06 | 2020-01-27 | 2020-01-24 |  | Michael Shiraz | Brittany Pool
General Ledger Balances | 20 | 2019-12-15 | 2020-01-27 | 2020-01-24 |  | Zeb Z | Brandi McDonald
General Ledger Detail for January | 33 | 2019-12-15 | 2020-02-13 | 2020-02-05 |  | Zeb Z | Brandi McDonald
Outstanding Checks for Revenue | 49 | 2020-01-06 | 2020-03-05 | 2020-03-02 |  | Heath Cameron | Courtney Roach
Revenue Owner Subledgers | 51 | 2020-01-06 | 2020-03-05 | 2020-03-02 |  | Heath Cameron | Courtnie Vinson
AR Open Items | 54 | 2020-01-13 | 2020-03-05 | 2020-03-02 |  | Zeb Z | Kathleen K
AP Open Items | 57 | 2020-01-14 | 2020-03-05 | 2020-03-02 |  | Quorum Support | Laurel Suits
Outstanding Checks for AP | 52 | 2020-01-06 | 2020-03-03 | 2020-03-02 |  | Quorum Support | Courtney Roach
Setup |  | Mapping | Conversion Date |  | Manual Clean Up Required? | Data Services Responsible Party | Business Responsible Party | Completion Date
Well Completion/Properties/DOI Xref | 46 | 2019-12-16 | 2020-03-05 | 2020-03-02 |  | Heath Cameron | Courtnie Vinson
Direct Revenue Input Links | 47 | 2019-12-16 | 2020-03-05 | 2020-03-02 |  | Heath Cameron | Courtnie Vinson
DOI Accounting | 48 | 2019-12-16 | 2020-03-05 | 2020-03-02 |  | Heath Cameron | Courtnie Vinson
Flow Grids | 66 | 2020-01-15 | N/A | 2020-03-02 |  | Heath Cameron | Kathleen K
Revenue Tax Set Up | 56 | 2020-01-20 | 2020-03-05 | 2020-03-02 |  | Heath Cameron | Courtnie Vinson
Payout Setup | 64 | 2020-02-10 | 2020-03-18 | 2020-03-02 |  | Heath Cameron | Courtnie Vinson
Historical Data |  | Mapping | Conversion Date |  | Manual Clean Up Required? | Data Services Responsible Party | Business Responsible Party | Completion Date
General Ledger Detail | #N/A | #N/A | #N/A |  |  | #N/A | #N/A
AR Open Item History | 55 | 2020-01-13 | 2020-01-20 |  |  | Zeb Z | Kathleen K
Depreciation Balances | 35 | 2020-01-02 | 2020-01-10 |  | Yes - despreciation to property level | Quorum Support | Courtney Roach
AP Payment History | 58 | 2020-01-20 | 2020-01-27 |  |  | Zeb Z | Laurel Suits
JIB Owner History | 61 | 2020-01-27 | N/A |  |  | Quorum Support | Kathleen K
Revenue Check History | 62 | 2020-02-03 | 2020-02-07 |  |  | Heath Cameron | Courtnie Vinson
Formulas:
Mapping = VLOOKUP([Masters],Detail!A:N,8,0)
Conversion Date = VLOOKUP([Masters],Detail!A:N,14,0)
Data Pull = VLOOKUP([Masters],Detail!A:O,15,0)

## Overview
(1) | Revamp JAG DOA to allow PE employee approvals. Invoices with pricebook issues will be disputed and deleted from JAG OI.
Disputed invoices - vendor will need to resubmit into PAR OI. JAG PB to be loaded into PE OI.
(2) | Cutoff JAG OI submissions. JAG employees will continue to code invoices to zero prior to final JIB run on 2.26.2020.
Disputed invoices - vendor will need to resubmit into PAR OI. JAG PB to be loaded into PE OI.
(3) | When JAG completes all Jan processing (around 2/4), PE to load all detail for Jan (by 2/6). PE will also load balances as of 12/31/2019
Post close entry to cover time period 1/1/2020 thru 1/10/2020.
(4) | Jan accruals to be posted first week of Feb by PE employees
CAPEX - Need all properties. Historical actuals. Field cost estimates. Development activity. GWI.
LOE - Need all properties. Historical actuals. BOE. GWI.
Revenue - Need all properties. Daily production. Contract information. NRI. Purchasers. Shrink/Yield.
G&A - Payroll. Rent. Consulting fees. Insurance. Software fees.
Leasing (maybe quarter in March?)
Derivatives - convert all outstanding trades to Mobius platform.
(5) | JAG will track Jan volumes. PAR to obtain weekly snapshots.
All wells, meters, etc will need to convert into PAR P2 in Jan.
Need info on reporting method for management visiblity.
January production PR, Tax, GLO, UT, and P18 reports to be filed by Parsley.
(6) | Starting Feb 1 all JAG volumes will be entered into PE instance of P2.
Production and regulatory reporting will occur on a combined basis by PE.
(7) | JAG Jan gas booked on two month lag (PAR books on one month). Jan JAG gas entries to be posted between 3/10 thru 3/15.
JAG Feb gas entries to be post on one month lag (like PAR normal process).
JAG Jan JIB 2.4.2020
JAG Revenue 2.25.2020, Jan Oil, Dec Gas
JAG Revenue 2.28.2020 Jan Gas
Open Invoice (2)
JAG OI Final Import 2.20.2020
Final JAG JIB 2.26.2020 (Feb Acct)
Final AP run 2.28.20
First PE Revenue Run Feb Oil, Feb Gas
First combine JIB run 3.23.2020 (Mar Acct)
GL Load – JAG Processes (3)
GL Load – JAG Processes (3)
Month Close Entries - PE
Fixed Assets - PE
Fixed Assets - PE
JAG AP
JAG Dec JIB 1.03.20
JAG Jan Revenue 1.24.20, Dec Oil, Nov Gas
Open Invoice (1)
Month Close Entries – JAG Dec Actg
Month Close Entries – PE Jan Actg (4)
Month Close Entries – PE (4)
Production Volumes - PE (6)
Load Historical GL Thru 12/31

## Pivot of Detail
Critical Path | (All)
Item # | (All)
Data Pull | Conversion/SetUp | Event
2020-01-02 | Cost Center, Properties, Wells, Cost Center Hierarchy | Compressor - Lease Use
2020-01-02 | Cost Center, Properties, Wells, Cost Center Hierarchy | Load Property Header Data in all key systems effected by conversion
2020-01-02 | Cost Center, Properties, Wells, Cost Center Hierarchy | Well & Meter Mapping
2020-01-02 | Cost Center, Properties, Wells, Cost Center Hierarchy | Hierarchy/Acquisition Codes/Non Op Properties
2020-01-02 | New Buisness Unit Setup | Setup new Buisness Unit for the new JAG companies (historical and other companies TBA)
2020-01-02 | COA Conversion/Xref | Provide potential export from Excalibur.
2020-01-02 | Assign all cost center numbers | Look for duplicates
2020-01-02 | Assign all cost center numbers | Create cross reference between PAR and JAG data
2020-01-02 | All Non Well Properties (Batteries, Allocations, Gathering Sys, etc.) | All Non Well Properties (Batteries, Allocations, Gathering Sys, AFE specials, etc.)
2020-01-24 | AFE Master | AFE Type use PE type
2020-01-24 | AFE Master | AFE App Script Open AFE's
2020-01-24 | AFE Master | Assign Numbers and plan to use JAG number with id.
2020-01-24 | AFE Master | Property AFE Xref
2020-01-24 | AFE Master | Load AFE Budget for Open AFEs?
2020-01-24 | Asset Master | Initial Acq Date
2020-01-24 | Asset Master | Load Asset IDs
2020-01-24 | Business Associates Master Land NRI | Assign Numbers and Status
2020-01-24 | Business Associates Master Land NRI | Detail for New Owners
2020-01-24 | Business Associates Master GWI Land | GWI Owner New Number
2020-01-24 | Business Associates Master GWI Land | GWI Owners Duplicates
2020-01-24 | Business Associates Master GWI Land | JIB BAs
2020-01-24 | Business Associates Master GWI Land | JIB Owner Netting Master
2020-01-24 | Business Associates Master Risk | Payment Terms
2020-01-24 | Business Associates Master Risk | Payment Type
2020-01-24 | Business Associates Master Risk | Vendor Different Duplicates
2020-01-24 | Business Associates Master Risk | Vendor Duplicates
2020-01-24 | Business Associates Master Risk | Vendor X Reference
2020-01-24 | Business Associates Master Risk | Vendors/Purchasers/Etc.
2020-01-24 | Business Associates Master Risk | Quorum Load into Salesforce
2020-01-24 | Business Associates Master Risk | Detail for New Vendors
2020-01-24 | Division of Interest (JIB) | JIB DOI (Current)
2020-01-24 | Division of Interest (JIB) | JIB DOI (Non-Current)
2020-01-24 | DocVue remaining history | Doc Vue History for pre-OI History
2020-01-24 | General Ledger Balances | Load Initial Balances
2020-01-24 | Inventory Stock Item Master | Convert Asset Master
2020-01-24 | JIB Cost Allocations | Allocations
2020-01-24 | Open Invoice History | Header: Vendor #, Invoice #, Invoice Date ( No Coding)
2020-01-24 | Open Invoice History | Historical Cutover 1 of 2
2020-01-24 | Open Invoice History | Open Ticket Identify Vendors Resubmit everything in flux
2020-01-24 | Open Invoice History | PE OT Vendors will auto convert to PE/JAG Vendors
2020-01-24 | Open Invoice History | Vendor Cross Reference
2020-01-24 | Open Invoice History | Historical Cutover 2 of 2
2020-01-24 | Open Invoice Price Books | Load PriceBooks for JAG
2020-01-24 | Non-Op Wells | Non-Op Wells
2020-01-24 | Business Associates Master Land | Quorum Load into Salesforce
2020-02-05 | Depreciation Balances | Module History/Spreadsheet History
2020-02-05 | JIB Cost Allocations | Allocations before 2.25.2019 PAR JIB run. Will Duel Maintain Allocations.
2020-02-05 | General Ledger Detail for January | Load January Activity
2020-02-05 | General Ledger History | All Activity thru 12/31. Put into company 925
2020-02-05 | Review and Load New Master Data that Changed | BAs, Cost Centers, AFEs, Properties, JIB DOIs
2020-03-02 | AP Open Items | Load AP Sub Ledger
2020-03-02 | AP Payment History | AP History
2020-03-02 | AR Open Item History | Accounts Receivable History
2020-03-02 | AR Open Items | Load Sub Ledger & Ledger
2020-03-02 | Business Associates Master Risk | Incremental Load
2020-03-02 | Cost Center, Properties, Wells, Cost Center Hierarchy | Incremental Load
2020-03-02 | Direct Revenue Input Links | Link Purchaser to active DOI
2020-03-02 | Division of Interest (Revenue) | Revenue DOI (Current)
2020-03-02 | Division of Interest (Revenue) | Revenue DOI (Non-Current)
2020-03-02 | Division of Interest (Revenue) | Revenue Market Bearer Groups
2020-03-02 | DOI Accounting | Revenue DOI APO/BPO
2020-03-02 | Flow Grids | Handled by P2 Intergration
2020-03-02 | JIB Owner History | JIB Owner History (if available)
2020-03-02 | Joint Interest Billing | Overhead
2020-03-02 | Joint Interest Billing | Prepaid Well Costs
2020-03-02 | Leasing | Leasing
2020-03-02 | Marketing | Notify Purchasers of New Contact/Remittance Information
2020-03-02 | OPPE | Prepaids - Obtain detailed spreadsheets. To be loaded with other beginning balances.
2020-03-02 | Revenue Check History | Revenue History
2020-03-02 | Revenue History | Historical Escheats filings
2020-03-02 | Revenue History | Revenue Severance Tax Reporting History. Only if in Excalibur.
2020-03-02 | Revenue Tax Set Up | RRC ID's & Current Drilling Permit # (TS010)
2020-03-02 | Revenue Tax Set Up | State Reporting Set Up
2020-03-02 | Well Completion/Properties/DOI Xref | Well Completion Set Up (DOI Accounting Rules)
2020-03-02 | Payout Setup | Master data setup
2020-03-02 | Payout Setup | Historical balances
2020-03-02 | Outstanding Checks for AP | Convert OS Checks/Keep Open Year
2020-03-02 | Revenue Owner Subledgers | Revenue Owner Payable - Minimum Pay
2020-03-02 | Revenue Owner Subledgers | Revenue Owner Payable - Suspense by Owners (History)
2020-03-02 | Outstanding Checks for Revenue | Convert OS Checks/Keep Open Year
2020-03-02 | Business Associates Master Land | Incremental Load
2020-03-02 | Production Volumes | Load Janaury Statements-Reconcile
2020-03-02 | General Ledger Detail for Feb | Load February Activity
Grand Total

## Detail
Production
BA Risk
BA Land / DOI
QCFS
QRA
DO
Financial/Leasing
2019-12-12
Conversion/SetUp | Item # | Critical Path | DE? | Technical Person | Responsible Party | Conversion Month | Mapping | Mapping Complete | Mapping Status | Conversion Logic Complete | Test Run 1 | Final Test (PRD Data) | Conversion | Data Pull | Dependent On | Upload Method | Welland Sandbox Table(s) | PRD Table(s) | Event
Batteries | 1 | Y | Y | Heath Cameron | Taylor Bishop | December | 2019-12-02 | 2019-12-09 | To be Finished by 12/13 | 2019-12-31 | 2020-01-01 | 2020-01-02 | 2020-01-06 | 2020-01-02 | None | Quorum Excel Upload |  |  | Needed before MDM push.
Assign all cost center numbers | 2 | Y | Y | Heath Cameron | Taylor Bishop | December | 2019-11-25 | 2019-12-04 | Closed 12/12/2019 | 2019-12-30 | 2020-01-01 | 2020-01-08 | 2020-01-10 | 2020-01-02 | None | Quorum Excel Upload |  |  | Look for duplicates
Assign all cost center numbers | 2.1 | Y | Y | Heath Cameron | Taylor Bishop | December | 2019-11-25 | 2019-12-04 | Closed 12/12/2019 | 2019-12-30 | 2020-01-01 | 2020-01-08 | 2020-01-10 | 2020-01-02 | None | Quorum Excel Upload |  |  | Create cross reference between PAR and JAG data
COA Conversion/Xref | 3 | Y | N | Heath Cameron/Zeb | Brandi McDonald | December | 2019-12-01 | 2019-12-09 | To be Finished by 12/16 | 2019-12-30 | 2020-01-01 | 2020-01-08 | 2020-01-10 | 2020-01-02 | None | Manual Input GUI |  |  | Provide potential export from Excalibur.
New Buisness Unit Setup | 4 | Y | N | N/A | Kara Wood | December | 2019-12-01 | 2019-12-09 | To be Finished by 12/16 | 2019-12-30 | 2020-01-01 | 2020-01-08 | 2020-01-10 | 2020-01-02 | None | Manual Input GUI |  |  | Setup new Buisness Unit for the new JAG companies (historical and other companies TBA)
All Non Well Properties (Allocations, Gathering Sys, etc.) | 5 | Y | Y | Heath Cameron | Taylor Bishop | December | 2019-12-02 | 2019-12-09 | To be Finished by 12/18 | 2019-12-30 | 2020-01-01 | 2020-01-08 | 2020-01-10 | 2020-01-02 | None | Quorum Excel Upload |  |  | All Non Well Properties (Allocations, Gathering Sys, AFE specials, etc.)
Cost Center, Properties, Wells, Cost Center Hierarchy | 6 | Y | N | Nick Bray | Taylor Bishop | January | 2019-12-02 | N/A |  | 2019-12-30 | 2020-01-01 | 2020-01-08 | 2020-01-10 | 2020-01-02 | Batteries | MDM |  |  | Load Property Header Data in all key systems effected by conversion
Treasury | 7 | Y | N | James Neblet | Courney Roach | January | 2020-01-10 |  | To be Finished by 12/18 | 2019-12-30 | 2020-01-01 | 2020-01-08 | 2020-01-10 |  |  | N/A |  |  | Need Banking Access After Close
Cost Center, Properties, Wells, Cost Center Hierarchy | 8 | Y | N | Alex Tran | Taylor Bishop | January | 2019-12-09 | 2019-12-13 |  | 2019-12-30 | 2020-01-01 | 2020-01-08 | 2020-01-10 | 2020-01-02 |  | N/A |  |  | Well & Meter Mapping
Cost Center, Properties, Wells, Cost Center Hierarchy | 8.1 | Y | N | Alex Tran | Taylor Bishop | January | 2019-12-09 | 2019-12-13 |  | 2019-12-30 | 2020-01-01 | 2020-01-08 | 2020-01-10 | 2020-01-02 |  | N/A |  |  | Compressor - Lease Use
Cost Center, Properties, Wells, Cost Center Hierarchy | 8.2 | Y | Y | Heath Cameron | Taylor Bishop | January | 2019-12-09 | 2019-12-13 |  | 2019-12-30 | 2020-01-01 | 2020-01-08 | 2020-01-10 | 2020-01-02 |  | Quorum Excel Upload |  |  | Hierarchy/Acquisition Codes/Non Op Properties
Business Associates Master Risk | 9 | Y | Y | Davison Oliver | Josh Owens | January | 2019-12-02 | 2019-12-12 | To be Finished by 12/13 | 2019-12-30 | 2020-01-01 | 2020-01-08 | 2020-01-10 | 2020-01-02 | None | Salesforce |  |  | Vendors/Purchasers/Etc.
Business Associates Master Risk | 9.1 | Y | Y | Davison Oliver | Josh Owens | January | 2019-12-10 | 2019-12-16 |  | 2019-12-30 | 2020-01-01 | 2020-01-08 | 2020-01-10 | 2020-01-02 |  | Salesforce |  |  | Detail for New Vendors
Business Associates Master GWI Land | 10 | Y | Y | Davison Oliver | Donald Harrell | January | 2019-12-02 | 2019-12-09 | To be Finished by 12/18 | 2020-01-14 | 2020-01-16 | 2020-01-23 | 2020-01-27 | 2020-01-24 | None | Salesforce |  |  | JIB BAs
Business Associates Master GWI Land | 10.1 | Y | Y | Davison Oliver | Donald Harrell | January | 2019-12-02 | 2019-12-09 | To be Finished by 12/18 | 2020-01-14 | 2020-01-16 | 2020-01-23 | 2020-01-27 | 2020-01-24 | None | Salesforce |  |  | GWI Owners Duplicates
Business Associates Master GWI Land | 10.2 | Y | Y | Davison Oliver | Donald Harrell | January | 2019-12-02 | 2019-12-09 | To be Finished by 12/18 | 2020-01-14 | 2020-01-16 | 2020-01-23 | 2020-01-27 | 2020-01-24 | None | Salesforce |  |  | GWI Owner New Number
Business Associates Master Land NRI | 11 | Y | Y | Davison Oliver | Donald Harrell | January | 2019-12-02 | 2019-12-09 | To be Finished by 12/18 | 2020-01-14 | 2020-01-16 | 2020-01-23 | 2020-01-27 | 2020-01-24 | None | Salesforce |  |  | Assign Numbers and Status
Non-Op Wells | 12 | Y | Y | Heath Cameron | Taylor Bishop | December | 2019-12-02 | 2019-12-09 | To be Finished by 12/20 | 2020-01-14 | 2020-01-16 | 2020-01-23 | 2020-01-27 | 2020-01-24 | BAs | Quorum Excel Upload |  |  | Non-Op Wells
AFE Master | 13 | Y | N | Quorum Support | Kathleen K | January | 2019-12-02 | 2019-12-09 | To be Finished by 12/17 | 2020-01-14 | 2020-01-16 | 2020-01-23 | 2020-01-27 | 2020-01-24 |  | AFE App |  |  | AFE Type use PE type
AFE Master | 13.1 | Y | N | Quorum Support | Kathleen K | January | 2019-12-02 | 2019-12-09 | To be Finished by 12/17 | 2020-01-14 | 2020-01-16 | 2020-01-23 | 2020-01-27 | 2020-01-24 |  | AFE App |  |  | Assign Numbers and plan to use JAG number with id.
Business Associates Master GWI Land | 14 | Y | Y | Davison Oliver | Kathleen K | January | 2019-12-09 | 2019-12-10 | Need more information | 2020-01-14 | 2020-01-16 | 2020-01-23 | 2020-01-27 | 2020-01-24 |  | Salesforce |  |  | JIB Owner Netting Master
Inventory Stock Item Master | 15 | N | N | Quorum Support | Kevin Hays | January | 2019-12-09 | 2019-12-11 | Need more information | 2020-01-14 | 2020-01-16 | 2020-01-23 | 2020-01-27 | 2020-01-24 |  | Manual Input GUI |  |  | Convert Asset Master
Business Associates Master Risk | 16 | Y | Y | Davison Oliver | Josh Owens | January | 2019-12-02 | 2019-12-12 | To be Finished by 12/13 | 2020-01-14 | 2020-01-16 | 2020-01-23 | 2020-01-27 | 2020-01-24 | None | Salesforce |  |  | Vendor Duplicates
Business Associates Master Risk | 16.1 | Y | Y | Davison Oliver | Josh Owens | January | 2019-12-02 | 2019-12-12 | To be Finished by 12/13 | 2020-01-14 | 2020-01-16 | 2020-01-23 | 2020-01-27 | 2020-01-24 | None | Salesforce |  |  | Vendor Different Duplicates
Business Associates Master Risk | 16.2 | Y | Y | Davison Oliver | Josh Owens | January | 2019-12-02 | 2019-12-12 | To be Finished by 12/13 | 2020-01-14 | 2020-01-16 | 2020-01-23 | 2020-01-27 | 2020-01-24 | None | Salesforce |  |  | Vendor X Reference
AFE Master | 17 | Y | N | Quorum Support | Kathleen K | January | 2019-12-10 | 2019-12-13 |  | 2020-01-14 | 2020-01-16 | 2020-01-23 | 2020-01-27 | 2020-01-24 |  | AFE App |  |  | Property AFE Xref
Business Associates Master Land NRI | 18 | Y | Y | Davison Oliver | Donald Harrell | January | 2019-12-10 | 2019-12-16 |  | 2020-01-14 | 2020-01-16 | 2020-01-23 | 2020-01-27 | 2020-01-24 |  | Salesforce |  |  | Detail for New Owners
Business Associates Master Risk | 19 | Y | Y | Davison Oliver | Josh Owens | January | 2019-12-10 | 2019-12-16 |  | 2020-01-14 | 2020-01-16 | 2020-01-23 | 2020-01-27 | 2020-01-24 |  | Salesforce |  |  | Payment Terms
Business Associates Master Risk | 19.1 | Y | Y | Davison Oliver | Josh Owens | January | 2019-12-10 | 2019-12-16 |  | 2020-01-14 | 2020-01-16 | 2020-01-23 | 2020-01-27 | 2020-01-24 |  | Salesforce |  |  | Payment Type
General Ledger Balances | 20 | N | Y | Zeb Z | Brandi McDonald | January | 2019-12-15 | 2020-01-13 |  | 2020-01-14 | 2020-01-16 | 2020-01-23 | 2020-01-27 | 2020-01-24 |  | Database to Database | [STG].[ GENERALJOURNALDETAIL_CONV] | [dbo].[ GENERALJOURNALDETAIL_CONV] | Load Initial Balances
Business Associates Master Risk | 21 | Y | Y | Alyson Carralez | Josh Owens | January | 2019-12-10 | 2019-12-16 |  | 2020-01-14 | 2020-01-16 | 2020-01-23 | 2020-01-27 | 2020-01-24 |  | Salesforce |  |  | Quorum Load into Salesforce
Business Associates Master Land | 22 | Y | Y | Alyson Carralez | Wade Potts | January | 43809 | 43815 |  | 43844 | 43846 | 43853 | 2020-01-27 | 2020-01-24 |  | Salesforce |  |  | Quorum Load into Salesforce
JIB Cost Allocations | 23 | Y | Y | Quorum Support | Kathleen K | January | 2019-12-12 | 2019-12-18 |  | 2020-01-14 | 2020-01-16 | 2020-01-23 | 2020-01-27 | 2020-01-24 |  | Script |  |  | Allocations
Division of Interest (JIB) | 24 | Y | Y | Davison Oliver | Donald Harrell | February | 2019-12-16 | 2019-12-30 |  | 2020-01-14 | 2020-01-16 | 2020-01-23 | 2020-01-27 | 2020-01-24 |  | Quorum Excel Upload |  |  | JIB DOI (Current)
Division of Interest (JIB) | 24.1 | Y | N | Davison Oliver | Donald Harrell | February | 2019-12-16 | 2019-12-30 |  | 2020-01-14 | 2020-01-16 | 2020-01-23 | 2020-01-27 | 2020-01-24 |  | Quorum Excel Upload |  |  | JIB DOI (Non-Current)
AFE Master | 25 | Y | Y | Quorum Support | Kathleen K | January | 2019-12-16 | 2019-12-31 |  | 2020-01-14 | 2020-01-16 | 2020-01-23 | 2020-01-27 | 2020-01-24 |  | AFE App |  |  | AFE App Script Open AFE's
AFE Master | 25.1 | Y | N | Quorum Support | Kathleen K | January | 2019-12-16 | 2019-12-31 |  | 2020-01-14 | 2020-01-16 | 2020-01-23 | 2020-01-27 | 2020-01-24 |  | AFE App |  |  | Load AFE Budget for Open AFEs?
Asset Master | 26 | N | N | Quorum Support | Courtney Roach | January | 2019-12-19 | 2019-12-31 |  | 2020-01-14 | 2020-01-16 | 2020-01-23 | 2020-01-27 | 2020-01-24 |  | Manual Input GUI |  |  | Load Asset IDs
Open Invoice History | 27 | Y | N | Michael Shiraz | Kathleen K | January | 2020-01-06 | 2020-01-20 |  | 2020-01-14 | 2020-01-16 | 2020-01-23 | 2020-01-27 | 2020-01-24 |  | N/A |  |  | PE OT Vendors will auto convert to PE/JAG Vendors
Open Invoice History | 27.1 | Y | N | Michael Shiraz | Kathleen K | January | 2020-01-06 | 2020-01-20 |  | 2020-01-14 | 2020-01-16 | 2020-01-23 | 2020-01-27 | 2020-01-24 |  | N/A |  |  | Vendor Cross Reference
Open Invoice History | 27.2 | Y | N | Michael Shiraz | Kathleen K | January | 2020-01-06 | 2020-01-20 |  | 2020-01-14 | 2020-01-16 | 2020-01-23 | 2020-01-27 | 2020-01-24 |  | N/A |  |  | Historical Cutover 1 of 2
Open Invoice History | 27.3 | Y | N | Michael Shiraz | Kathleen K | January | 2020-01-06 | 2020-01-20 |  | 2020-01-14 | 2020-01-16 | 2020-01-23 | 2020-01-27 | 2020-01-24 |  | N/A |  |  | Header: Vendor #, Invoice #, Invoice Date ( No Coding)
Open Invoice History | 27.4 | Y | N | Michael Shiraz | Kathleen K | January | 2020-01-06 | 2020-01-20 |  | 2020-01-14 | 2020-01-16 | 2020-01-23 | 2020-01-27 | 2020-01-24 |  | N/A |  |  | Open Ticket Identify Vendors Resubmit everything in flux
DocVue remaining history | 28 | Y | N | Michael Shiraz | Kathleen K | January | 2020-01-06 | 2020-01-20 |  | 2020-01-14 | 2020-01-16 | 2020-01-23 | 2020-01-27 | 2020-01-24 |  | N/A |  |  | Doc Vue History for pre-OI History
Open Invoice History | 29 | Y | N | Michael Shiraz | Kathleen K | January | 2020-01-06 | 2020-01-20 |  | 2020-01-14 | 2020-01-16 | 2020-01-23 | 2020-01-27 | 2020-01-24 |  | N/A |  |  | Historical Cutover 2 of 2
Open Invoice Price Books | 30 | N | N | Michael Shiraz | Brittany Pool | January | 2020-01-06 | 2020-01-20 |  | 2020-01-14 | 2020-01-16 | 2020-01-23 | 2020-01-27 | 2020-01-24 |  | N/A |  |  | Load PriceBooks for JAG
Asset Master | 31 | N | N | Quorum Support | Courtney Roach | January | 2019-12-19 | 2019-12-31 |  | 2020-01-14 | 2020-01-16 | 2020-01-23 | 2020-01-27 | 2020-01-24 |  | Manual Input GUI |  |  | Initial Acq Date
Production Volumes | 32 | N | N | Alex Tran | Taylor Bishop | February | 2019-12-15 | N/A |  | 2020-01-21 | 2020-01-23 | 2020-01-30 | 2020-02-01 |  |  | N/A |  |  | Load Full History
General Ledger Detail for January | 33 | N | Y | Zeb Z | Brandi McDonald | February | 2019-12-15 | 2020-01-13 |  | 2020-01-31 | 2020-02-04 | 2020-02-11 | 2020-02-13 | 2020-02-05 |  | Database to Database | [STG].[ GENERALJOURNALDETAIL_CONV] | [dbo].[ GENERALJOURNALDETAIL_CONV] | Load January Activity
General Ledger History | 34 | N | Y | Zeb Z | Brandi McDonald | February | 2019-12-15 | 2020-01-13 |  | 2020-02-05 | 2020-02-07 | 2020-02-14 | 2020-02-18 | 2020-02-05 |  | Database to Database | [STG].[ GENERALJOURNALDETAIL_CONV] | [dbo].[ GENERALJOURNALDETAIL_CONV] | All Activity thru 12/31. Put into company 925
Depreciation Balances | 35 | N | N | Quorum Support | Courtney Roach | February | 2020-01-02 | 2020-01-10 |  | 2020-01-24 | 2020-01-28 | 2020-02-04 | 2020-02-06 | 2020-02-05 |  | Manual Input GUI |  |  | Module History/Spreadsheet History
JIB Cost Allocations | 36 | Y | Y | Quorum Support | Kathleen K | February | N/A | N/A |  | 2020-01-24 | 2020-01-28 | 2020-02-04 | 2020-02-06 | 2020-02-05 |  | Manual Input GUI |  |  | Allocations before 2.25.2019 PAR JIB run. Will Duel Maintain Allocations.
Review and Load New Master Data that Changed | 37 | [8 empty] | 2020-01-24 | 2020-01-28 | 2020-02-04 | 2020-02-06 | 2020-02-05 |  | Manual Input GUI |  |  | BAs, Cost Centers, AFEs, Properties, JIB DOIs
Cost Center, Properties, Wells, Cost Center Hierarchy | 38 | Y | Y | Heath Cameron | Taylor Bishop | January | 2019-12-09 | 2019-12-13 |  | 2020-02-21 | 2020-02-25 | 2020-03-03 | 2020-03-05 | 2020-03-02 |  | Manual Input GUI |  |  | Incremental Load
Division of Interest (Revenue) | 39 | Y | Y | Davison Oliver | Donald Harrell | February | 2019-12-30 | 2020-01-13 |  | 2020-02-21 | 2020-02-25 | 2020-03-03 | 2020-03-05 | 2020-03-02 |  | Quorum Excel Upload |  |  | Revenue DOI (Current)
Division of Interest (Revenue) | 39.1 | Y | N | Davison Oliver | Donald Harrell | February | 2019-12-30 | 2020-01-13 |  | 2020-02-21 | 2020-02-25 | 2020-03-03 | 2020-03-05 | 2020-03-02 |  | Quorum Excel Upload |  |  | Revenue DOI (Non-Current)
Division of Interest (Revenue) | 39.2 | Y | N | Davison Oliver | Donald Harrell | February | 2019-12-30 | 2020-01-13 |  | 2020-02-21 | 2020-02-25 | 2020-03-03 | 2020-03-05 | 2020-03-02 |  | Quorum Excel Upload |  |  | Revenue Market Bearer Groups
Joint Interest Billing | 40 | N | N | Quorum Support | Kathleen K | February | 2020-01-02 | 2020-01-03 |  | 2020-02-21 | 2020-02-25 | 2020-03-03 | 2020-03-05 | 2020-03-02 |  | N/A |  |  | Overhead
Joint Interest Billing | 40.1 | N | N | Quorum Support | Kathleen K | February | 2020-01-02 | 2020-01-03 |  | 2020-02-21 | 2020-02-25 | 2020-03-03 | 2020-03-05 | 2020-03-02 |  | N/A |  |  | Prepaid Well Costs
Business Associates Master Risk | 41 | N | N | Davison Oliver | Josh Owens |  |  |  |  | 2020-02-21 | 2020-02-25 | 2020-03-03 | 2020-03-05 | 2020-01-24 |  | Salesforce |  |  | Incremental Load
Business Associates Master Risk | 41.1 | N | N | Davison Oliver | Josh Owens | [7 empty] | 2020-03-05 | 2020-02-05 |  | Salesforce |  |  | Incremental Load
Business Associates Master Land | 42 | N | N | Davison Oliver | Donald Harrell | [7 empty] | 2020-03-05 | 2020-02-05 |  | Salesforce |  |  | Incremental Load
Business Associates Master Land | 42.1 | Y | Y | Davison Oliver | Donald Harrell | January | 2019-12-30 | 2020-01-13 |  | 2020-02-21 | 2020-02-25 | 2020-03-03 | 2020-03-05 | 2020-03-02 |  | Salesforce |  |  | Incremental Load
Business Associates Master Risk | 43 | Y | Y | Davison Oliver | Josh Owens | January | 2019-12-30 | 2020-01-13 |  | 2020-02-21 | 2020-02-25 | 2020-03-03 | 2020-03-05 | 2020-03-02 |  | Salesforce |  |  | Incremental Load
Production Volumes | 44 | N | N | Alex Tran | Taylor Bishop | February | 2020-02-08 | N/A |  | 2020-02-21 | 2020-02-25 | 2020-03-03 | 2020-03-05 | 2020-03-02 |  | N/A |  |  | Load Janaury Statements-Reconcile
Marketing | 45 | N | N | N/A | Marketing Group | February | 2020-02-01 | N/A |  | 2020-02-21 | 43886 | 43893 | 2020-03-05 | 2020-03-02 |  | N/A |  |  | Notify Purchasers of New Contact/Remittance Information
Well Completion/Properties/DOI Xref | 46 | Y | Y | Heath Cameron | Courtnie Vinson | February | 2019-12-16 | 2020-01-03 |  | 2020-02-21 | 2020-02-25 | 2020-03-03 | 2020-03-05 | 2020-03-02 |  | Quorum Excel Upload |  |  | Well Completion Set Up (DOI Accounting Rules)
Direct Revenue Input Links | 47 | Y | N | Heath Cameron | Courtnie Vinson | February | 2019-12-16 | 2020-01-03 |  | 2020-02-21 | 2020-02-25 | 2020-03-03 | 2020-03-05 | 2020-03-02 |  | Quorum Excel Upload |  |  | Link Purchaser to active DOI
DOI Accounting | 48 | N | N | Heath Cameron | Courtnie Vinson | February | 2019-12-16 | 2020-01-03 |  | 2020-02-21 | 2020-02-25 | 2020-03-03 | 2020-03-05 | 2020-03-02 |  | Quorum Excel Upload |  |  | Revenue DOI APO/BPO
Outstanding Checks for Revenue | 49 | N | Y | Heath Cameron | Courtney Roach | February | 2020-01-06 | 2020-01-17 |  | 2020-02-21 | 2020-02-25 | 2020-03-03 | 2020-03-05 | 2020-03-02 |  | Quorum Excel Upload |  |  | Convert OS Checks/Keep Open Year
General Ledger Detail for Feb | 50 | N | Y | Heath Cameron | Brandi McDonald | March | 2019-12-15 | 2020-01-13 |  | 2020-02-21 | 2020-02-25 | 2020-03-03 | 2020-03-05 | 2020-03-02 |  | Database to Database | [STG].[ GENERALJOURNALDETAIL_CONV] | [dbo].[ GENERALJOURNALDETAIL_CONV] | Load February Activity
Revenue Owner Subledgers | 51 | N | Y | Heath Cameron | Courtnie Vinson | February | 2020-01-06 | 2020-01-17 |  | 2020-02-21 | 2020-02-25 | 2020-03-03 | 2020-03-05 | 2020-03-02 |  | Database to Database | STG.JSTG_MANL_JE_DETAIL | dbo.JSTG_MANL_JE_DETAIL | Revenue Owner Payable - Minimum Pay
Outstanding Checks for AP | 52 | N | Y | Quorum Support | Courtney Roach | February | 2020-01-06 | 2020-01-13 |  | 2020-02-19 | 2020-02-21 | 2020-02-28 | 2020-03-03 | 2020-03-02 |  | Manual Input GUI |  |  | Convert OS Checks/Keep Open Year
Revenue Owner Subledgers | 53 | Y | Y | Heath Cameron | Courtnie Vinson | February | 2020-01-06 | 2020-01-17 |  | 2020-02-21 | 2020-02-25 | 2020-03-03 | 2020-03-05 | 2020-03-02 |  | Database to Database | STG.JSTG_MANL_JE_DETAIL | dbo.JSTG_MANL_JE_DETAIL | Revenue Owner - Suspense by Owners (History)
AR Open Items | 54 | Y | N | Zeb Z | Kathleen K | February | 2020-01-13 | 2020-01-20 |  | 2020-02-21 | 2020-02-25 | 2020-03-03 | 2020-03-05 | 2020-03-02 |  | Quorum Excel Upload |  |  | Load Sub Ledger & Ledger
AR Open Item History | 55 | Y | N | Zeb Z | Kathleen K | February | 2020-01-13 | 2020-01-20 |  | 2020-02-21 | 2020-02-25 | 2020-03-03 | 2020-03-05 | 2020-03-02 |  | Database to Database | [STG].[CUSTOMEROPENITEMCONV] | [dbo].[CUSTOMEROPENITEMCONV] | Accounts Receivable History
Revenue Tax Set Up | 56 | N | N | Heath Cameron | Courtnie Vinson | February | 2020-01-20 | 2020-01-23 |  | 2020-02-21 | 2020-02-25 | 2020-03-03 | 2020-03-05 | 2020-03-02 |  | Quorum Excel Upload |  |  | State Reporting Set Up
Revenue Tax Set Up | 56.1 | N | N | Heath Cameron | Courtnie Vinson | February | 2020-01-20 | 2020-01-23 |  | 2020-02-21 | 2020-02-25 | 2020-03-03 | 2020-03-05 | 2020-03-02 |  | Quorum Excel Upload |  |  | RRC ID's & Current Drilling Permit # (TS010)
AP Open Items | 57 | Y | Y | Quorum Support | Laurel Suits | February | 2020-01-14 | 2020-01-24 |  | 2020-02-21 | 2020-02-25 | 2020-03-03 | 2020-03-05 | 2020-03-02 |  | Database to Database | STG.CHKRUNJRNL_CONV STG.CHKRUNJRNLITEM_CONV | dbo.CHKRUNJRNL_CONV dbo.CHKRUNJRNLITEM_CONV | Load AP Sub Ledger
AP Payment History | 58 | Y | N | Zeb Z | Laurel Suits | March | 2020-01-20 | 2020-01-27 |  | 2020-02-21 | 2020-02-25 | 2020-03-03 | 2020-03-05 | 2020-03-02 |  | Database to Database | STG.CHKRUNJRNL_CONV STG.CHKRUNJRNLITEM_CONV | dbo.CHKRUNJRNL_CONV dbo.CHKRUNJRNLITEM_CONV | AP History
Leasing | 59 | N | N | N/A | Calixo Balderas | March | 2020-01-27 | N/A |  | 2020-03-03 | 2020-03-05 | 2020-03-12 | 2020-03-16 | 2020-03-02 |  | N/A |  |  | Leasing
Revenue History | 60 | N | N | Heath Cameron | Courtnie Vinson | March | 2020-01-27 | 2020-01-31 |  | 2020-03-05 | 2020-03-09 | 2020-03-16 | 2020-03-18 | 2020-03-02 |  | N/A |  |  | Revenue Severance Tax Reporting History. Only if in Excalibur.
JIB Owner History | 61 | N | N | Quorum Support | Kathleen K | March | 2020-01-27 | N/A |  | 2020-03-05 | 2020-03-09 | 2020-03-16 | 2020-03-18 | 2020-03-02 |  |  |  |  | JIB Owner History (if available)
Revenue Check History | 62 | N | N | Heath Cameron | Courtnie Vinson | March | 2020-02-03 | 2020-02-07 |  | 2020-03-05 | 2020-03-09 | 2020-03-16 | 2020-03-18 | 2020-03-02 |  | Database to Database | STG.RTRN_CHK_RGSTR STG.RTRN_CHK_RGSTR_DETAIL STG.RTRN_CHK_RGSTR_ADJ_CTGY STG.RTRN_CHK_RGSTR_DETAIL_TAX | dbo.RTRN_CHK_RGSTR dbo.RTRN_CHK_RGSTR_DETAIL dbo.RTRN_CHK_RGSTR_ADJ_CTGY dbo.RTRN_CHK_RGSTR_DETAIL_TAX | Revenue History
Revenue History | 63 | N | N | Davison Oliver | Donald Harrell | March | 2020-02-04 |  |  | 2020-03-05 | 2020-03-09 | 2020-03-16 | 2020-03-18 | 2020-03-02 |  | N/A |  |  | Historical Escheats filings
Payout Setup | 64 | N | N | Heath Cameron | Courtnie Vinson | March | 2020-02-10 | 2020-02-14 |  | 2020-03-05 | 2020-03-09 | 2020-03-16 | 2020-03-18 | 2020-03-02 |  | Quorum Excel Upload |  |  | Master data setup
Payout Setup | 64.1 | N | N | Heath Cameron | Courtnie Vinson | March | 2020-02-10 | 2020-02-14 |  | 2020-03-05 | 2020-03-09 | 2020-03-16 | 2020-03-18 | 2020-03-02 |  | Quorum Excel Upload |  |  | Historical balances
OPPE | 65 | N | N | Quorum Support | Courtney Roach | February | 2020-01-14 | N/A |  | N/A | N/A | N/A | N/A | 2020-03-02 |  | N/A |  |  | Prepaids - Obtain detailed spreadsheets. To be loaded with other beginning balances.
Flow Grids | 66 | Y | N | Heath Cameron | Kathleen K | February | 2020-01-15 | N/A |  | N/A | N/A | N/A | N/A | 2020-03-02 |  | Manual Input GUI |  |  | Handled by P2 Intergration
Mobius Conversion | [6 empty] | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A
1099 for 2019 |  | N |  | Heath Cameron | Laurel Suits |  |  |  |  | 2020-03-05 | [5 empty] | N/A
1099 for two months |  | N |  | Heath Cameron | Laurel Suits |  |  |  |  | 2020-03-05 | [5 empty] | N/A
Formulas:
Final Test (PRD Data) = WORKDAY([Conversion], -2)
Test Run 1 = WORKDAY([Final Test (PRD Data)], -5)
Conversion Logic Complete = WORKDAY([Test Run 1], -2)

## Production Accounting Detail
Production
BA Risk
BA Land / DOI
QCFS
QRA
DO
Financial/Leasing
Conversion/SetUp | Item | Notes | Technical Person | Responsible Party | Conversion Month | Mapping | Mapping Complete | Conversion | Event
Creat xref for Product Code |  | Need Picklist - PA to map | [6 empty] | Completion Date Effective Items
Creat xref for Completion Type |  | Need Picklist - PA to map | [6 empty] | Completion Date Effective Items
Creat xref for Producing Method |  | Need Picklist - PA to map | [6 empty] | Completion Date Effective Items
Creat xref for Producting Status |  | Need Picklist - PA to map | [6 empty] | Completion Date Effective Items
Create xref for operator (primarily on non-op wells) |  | Need Picklist - PA to map | [6 empty] | Completion Date Effective Items
Create xref for Area (Basin) |  | Need Picklist - PA to map | [6 empty] | Completion Date Effective Items
Create xref for Power Method |  | Doesn't look like JP has this in P2 | [6 empty] | DDA under Location
Create xref for Field Group |  | Doesn't look like JP has this in P2 | [6 empty] | SWD Method (pipe or truck haul)
Well |  |  |  |  | December | 2019-11-25 | 2019-12-04 | 2019-12-07
Completion |  |  |  |  | December | 2019-11-25 | 2019-12-04 | 2019-12-07
Creat xref for Disposition |  | Need Picklist - PA to map | [6 empty] | Meter date effective item
Create xref for Purchaser |  | Need Picklist - PA to map | [6 empty] | Meter date effective item
Create xref for Gas Plant |  | Doesn't look like JP has this in P2 | [6 empty] | Meter date effective item
Create xref for Hauler |  | Doesn't look like JP has this in P2 | [6 empty] | Meter date effective item
Insert Gathering Sysems and create xref |  | Pull directly from JAG and assign new MID
Meters |  |  |  |  | December | 2019-12-01 | 2019-12-09 | 2019-12-15
Tanks |  |  |  |  | December | 2019-12-01 | 2019-12-09 | 2019-12-15
Equipment |  |  |  |  | January | 2019-12-02 | 2019-12-09 | 2020-01-27
Map Platform / Facility |  | Doesn't look like JP has this in P2 | [6 empty] | purchaser meter number / lease ID for allocations
Map / Insert SWD |  | Doesn't look like JP has this in P2 | [6 empty] | What SWD is the well going go?
Connections
Daily records
Monthly records
Historical allocated production data
Initialize tanks
Map POP Date / Initial Prod Date
Questions - Which field contains the POP date
Where is orientation stored?
Where do we want to store the historical field / area?
Where is the power method maintained? Can we get a spreadsheet?
How can we tell which wells / batteries are connected to SWD gathering and which wells have water hauled via truck?
Where can we get gas plant information?
Where can we get hauler information?
Where can we get purchaser meter numbers / lease ID information?